## Sheet1
Survey Timeline & Roles/Responsibilites
| Task | Due Date | Status | Person(s) Responsible | Notes
Preparation | Define survey purpose
Review existing data & determine if survey is necessary
Consider questions posed in the Survey Planning Doc (linked on OIRE website)
Discuss project with potential collaborators
Determine timing of survey, being sure to avoid potential conflicts (other surveys, holidays, etc.) - check with OIRE for other survey conflicts.
Building | Create survey instrument
Identify necessary demographic information & determine what can be embedded
Write email/reminder content/subject lines
Build survey instrument in Qualtrics or other survey software
Send preview link to survey
Review survey & identify any desired changes
Generate distribution list
Administration/Marketing | Response rate boosters: Secure incentives, create/hang posters, add links to portals, include blurbs in newsletters, etc.
Launch survey/Send initial email
Share first response rate update
Send first reminder email
Share second response rate update
Send second reminder email
Share third response rate update
Close survey
Analysis | Review/clean data
Analyze data
Flag any potentially reportable responses & share with approriate individuals/offices
Prepare reports or dashboards
Share results
Implement change