## Role Descriptions
Roles and Responsibilities
A Roles and Responsibilities document is a formal way of defining what each role is responsible for on a project team.
Project Role/Team | Responsibilities
Agile Coach | The Agile Coach acts as a coach for both the Development team and the Product Owner. The coach in a way acts as an enabler for proper communication between the Development Team and the Product Owner. The coach stays responsible to eliminate the obstacle between both the other roles.
Accessibility Lead | Primary project point-of-contact for accessibility questions or issues. Questions about the process can be sent to ICTCompliance@colorado.edu.
Accessibililty & Usability Test Lab | Tests accessibility and usability requirements. Signs off that web accessibility and usability requirements have been met.
Architect | Defines the overall tools and systems the project will create or change; Works with the Enterprise Architectual Review Board (E-ARB) drafting required documentation for their review, presents to E-ARB for approval
Business Analyst | Captures and documents requirements, process flows, and use cases. Fills out Security Review Questionnaire, working with PM and other team members. Creates test scripts
Budget Manager | Determines how funds are spent against OIT, UIS, or one-time project budget, tracks the expenses against the balance sheet, initiates and approves all purchases with the IT business office and suppliers, reconciles all invoices and provides regular updates on the budget to the sponsor. Involvement in Planning: this role provides input on procurement process, informs the procurement timeframe(s) for planning purposes, liaises with the PSC and develops a consolidated cross-campus budget view for the project to track against. Involvement in Execution: this role, in collaboration with the team of cross-campus IT budget managers as necessary, is responsible for initiating procurement and associated contracts with the PSC, providing procurement status updates to the sponsor, tracking expenses against budgets and forecasting burndown rates, approving procurements, reconciling invoices and providing regular budget and procurement updates to the sponsor, resource managers and steering committee.
CAB | Change Advisory Board. Reviews any project changes before they go into production
Communications Lead | Coordinate internal and external project communications
Customer Representative | Represent the user community by providing requirements, answering questions, and performing usability testing
Designer | Designs the solution(s) that will meet the requirements
Development Team | A development team is composed of professionals who do the hands-on work of completing the tasks in a sprint. This means development team members can be computer engineers, designers, writers, data analysts, or any other role needed to reach sprint goals.
Direct Line Supervisor | Signing off on use of resource for project planning and execution phases, is aware of project load versus operation load providing support to employee on priorities, Managing the overall workload. Pulling project load data from PMO when needed, aids PM in project planning phase as requested, ensure status and hours are being recorded within the UIS project Tool
Enterprise - Architecture Review Board | Projects would pass through architectural review as a gate in the planning process prior to execution. A cross campus group of architects (the E-ARB) would be convened and would serve as the core architectural review group (which would be augmented based on the specific project/solution being considered). At least 1 in-person meeting should occur in the review process for projects in the scope of IT Governance but review could be triggered through submission of artifacts through a standard form and pre-meeting interaction with members of the E-ARB.This group drives adherence to architectureal principals and standards as they are defined, aligns to existing service road maps, promotes re-use of shared services/architectures where appropriate
Executive Sponsor | Reviews Project Charter and provides input. Point of contact for project escalations. Advocates for or champions the project. Educates as a voice of the project to those who don't know about it or need information. Provides inputs as requested on Scope, Requirements, Risks, Roles, Funding, Reporting, and other project deliverables as needed. Encourages finalization of high-level requirements and scope by stakeholders across campuses. Gives the Project Manager authority and supports them per their role as defined in the Roles & Responsbilities matrix. Acknowledges escalation requests from Project Manager and commits to realistic response times
Finance & Business Operations | Confirms project funding and budget availability
Functional Lead | Supporting BA with gathering functional requirements, taking primary responsibility for appropriate customer level signoff, aid in translation of requirements into technical requirements with Technical lead or SME, aids in translating requirements timeline tasks with predecessors and work effort, aid in risk register definition and proactive mitigation, aid in assessing communication needs for project with customers and team, ensure status and hours are being recorded within the UIS Project Tool, aids PM in coordination of tasks with customer
Identity Management | Based on requirements, ask questions and gathers data about authentication and authorization needs, aids PM with creating associated requirements, tasks, and estimates. Aids PM with coordinating across campuses due to various Identity management solution to ensure this function is designed appropriately for the project's goals and scope.
Implementer | Implements the solution per the Design, moving into Production
Integrator | Integrates the new product or service with existing systems
Networking | Provides operational requirements, designs solutions, and implements network services
Organizational Change Mgr | Responsible for defining the process, tools, and techniques to manage the people side of the changes the project will be making This includes communication, training, and stakeholder management strategies and plans, as well as assessments to understand the organizational landscape
Product Owner | The Product Owner (PO) is a member of the Agile Team responsible for defining Stories and prioritizing the Team Backlog to streamline the execution of program priorities while maintaining the conceptual and technical integrity of the Features or components for the team. Product Owner is a key participant in the Sprint related activities. Works closely with the Development Team in explaining the Items, their scope and the value it holds.
Project Administrator | Assists Project Managers with project administration and organization on large and high priority projects as defined by CU IT Governance.
Project Manager | Responsible for meeting project objectives, managing project issues and risks, and controlling schedule, cost, and scope
Program Manager | Manage program staff and project managers by providing leadership, vision and have authority to make changes to programs and projects on large and high priority projects as defined by CU IT Governance. Please see IT Governance Program Manager role description for more detail
Quality Assurance (QA) Tester: | Reviews user requirements documents to ensure that requirements are testable and works collaboratively with business units to execute and validate test cases based upon system requirements.
Release Manager | Coordinate with the functional and technical teams on the type of maintenance window that will be required, Coordinating with the Communication Manager on the messaging for the release, Coordinate with the service owner on the release plan and impact to the service , Development of the work plan that includes preparation, technical migration and functional testing steps, Leads work plan review meetings, Approval of the work plan by service owner, Managing the execution of the work plan during the go-live maintenance window, Coordinating with the Help Desk on plan changes and provide documentation as needed, Setting up and managing the post go-live command center, if applicable, and/or advises on resources needed during warranty period. Working closely with the PM to ensure tasks are entered into TD
Security Lead | Defines security requirements, constraints, and tests for projects. Involved in: Vendor analysis and review, Contract Review, Data Governance Process Facilitation, Penetration Testing analysis, planning, and execution, General Architectural Review
Service Center | Defines requirements for supporting customer inquiries, issues, and support once project is live
Service Manager | Primary POC for a service. Has final responsibility for decision making or escalations regarding the service
Solutions Architect* | The Solutions Architect, working off of Requirements, Security Reviews, Data Governance Reviews, and Accessibility Reviews partners with the Technical Lead to design and define architectural artifacts for the project such as: Network Diagrams, Data Flow/Integrations Diagrams, Environment Diagrams, and Authentication/Authorization & User Provisioning Diagrams. This role will aid in presenting to the Enterprise Architecture Review Board (E-ARB) as well as serve as primary project liaison to the E-ARB during the execution phase. This position will aid the technical team and PM with task definition and sequencing of work as requested.
Sponsor, Business | Provides funding and requirements for the project from outside IT. Champions the project across campus or campuses. Primary escalation point outside IT organization.
Sponsor, (within OIT or UIS) | Champions the project, confirms goals and objectives, stays current on status, and makes final decisions. Represents projects within campus level-governance committees. Primary escalation point in OIT.
Stakeholder | Individuals and organizations that are actively involved in the project or whose interests may be affected by the project
Steering Committee | They approve deliverables, resolve issues, set policy, and approve changes for the project
Subject Matter Expert | Provides guidance and information to the team and may assist with requirements, design, or testing
Team / Tech Lead | Produce detailed planning, provide progress reports, ensure quality, and provide technical leadership for one or more teams. Aids team with creating unit test scripts
Technical Analyst | Reviewing documented business/functional requirements and translating to technical requirements, using methods appropriate to specific project to document technical requirements, outlining potential impacts of system or process changes, documenting requirement traceability, in terms of how non-functional requirements will be tested, aid in translation of requirements into project timeline of tasks with predecessors and work effort, aid in risk register definition and proactive mitigation
Test Lead | Defining and implementing the testing methodology for cross-functional and non cross-functional projects and for participating in, and supporting all required testing activities such as Unit testing, Integrated System Testing, UAT, Load Testing , Accessibility Testing and Security Testing to ensure all process controls are adhered to and completed in a timely and cost effective manner.
Test Coordinator | Serves as the facilitator and coordinator of testing between upstream and downstream teams to ensure effective distribution of testing tasks with minimum overlap. Communicates effectively and timely with customers, team members, and management regarding the status of test case execution. Updates or develops test documentation as necessary and ensures testing deliverables are completed within defined schedule.
Tester | Defines testing approach and coordinates or performs one or more types of testing
Training Lead | Creates and provides internal training for the project team and/or the OIT or UIS organization.